JP HERITAGE E-PORTAL

Design Rebrand — Implementation Plan

Version 1.0  ·  February 2026  ·  Confidential

Executive Summary

This document outlines the high-level implementation plan for transitioning the JP Heritage E-Portal from its current green-dominant design system to a deep navy blue palette, consolidating the brand name to "JP Heritage" throughout, unifying the header treatment across all pages, and resolving the accessibility contrast failure on the Send Transfer button. The plan is structured in 8 sequential phases spanning approximately 10 working days.

Scope: 4 targeted changes — (1) Navy blue color system (2) Brand name consolidation (3) Header unification (4) Button contrast fix

Implementation Roadmap Overview

The table below summarizes all phases, their timeline, scope, and category. Phases are ordered by dependency — accessibility fixes first, then the design token foundation, then surface-level visual changes.

| Phase | Name | Timeline | Scope | Type |
| --- | --- | --- | --- | --- |
| Phase 1 | Accessibility Fix | Day 1 | Button contrast, text legibility | Immediate |
| Phase 2 | Design Tokens | Days 1–2 | CSS variables, global color constants | Foundation |
| Phase 3 | Brand Rename | Days 2–3 | All text, meta, legal copy, logo alt text | Quick Win |
| Phase 4 | Header Unification | Days 3–4 | Navbar, login header, sidebar top section | Quick Win |
| Phase 5 | Login Page Restyle | Days 4–5 | Background, card, button, footer | Core |
| Phase 6 | Dashboard Restyle | Days 5–7 | Sidebar, cards, chart area, stat blocks | Core |
| Phase 7 | Inner Pages | Days 7–9 | Transfer, bills, accounts, settings pages | Core |
| Phase 8 | QA & Accessibility | Days 9–10 | WCAG audit, cross-browser, responsive checks | Final |

Phase 1 — Accessibility Fix: Button Contrast  (Day 1)

This is the single highest-priority change. The Send Transfer button and the Sign In button both suffer from insufficient foreground-to-background contrast, violating WCAG 2.1 AA (minimum 4.5:1 for normal text, 3:1 for large text). This must be resolved before or alongside any other changes.

Problem

Dark olive/charcoal text is being rendered on a dark green button background. The resulting contrast ratio is estimated at approximately 2.1:1 — well below the WCAG AA threshold of 4.5:1. The button label is effectively invisible in certain lighting conditions and for users with visual impairments.

Fix

Change all primary action button text to white (#FFFFFF) and update the button background to JP Heritage Navy (#0D2545). This combination yields a contrast ratio of approximately 15:1, far exceeding WCAG AAA requirements.

/* BEFORE — fails WCAG AA */ .btn-primary { background-color: #1C4A1C; /* dark green */ color: #2D3A2D; /* dark text — contrast ~2.1:1 ✗ */ } /* AFTER — passes WCAG AAA */ .btn-primary { background-color: #0D2545; /* JP Heritage Navy */ color: #FFFFFF; /* white text — contrast ~15:1 ✓ */ }

Affected Components

- Login page — Sign In button

- Money Transfer page — Send Transfer button

- Any other primary CTA buttons across the portal (audit all pages)

WCAG Contrast Reference

| UI Element | Before | After | WCAG AA Ratio |
| --- | --- | --- | --- |
| Sign In button | Dark text / Dark green bg | White text / #0D2545 bg | 12.5:1 ✓ |
| Send Transfer button | Dark text / Dark green bg | White text / #0D2545 bg | 12.5:1 ✓ |
| Body text on card | Dark text / White bg | Dark text / #F0F4FA bg | 14.3:1 ✓ |
| Label text on navy | N/A | White / #0D2545 | 15.0:1 ✓ |
| Gold accent on navy | N/A | #B8960C / #0D2545 | 7.2:1 ✓ |

Phase 2 — Design Token Foundation  (Days 1–2)

Before touching any UI components, establish a centralized CSS custom property (design token) system. This ensures that all subsequent color changes are made in one place and propagate automatically to every component. This is the architectural foundation everything else depends on.

New Color Palette

The following tokens replace all hardcoded green values. They map directly to the JP Heritage navy brand identity while preserving functional colors for positive/negative financial states.

| Swatch | Token Name | Usage |
| --- | --- | --- |
| #0D2545 | Navy Primary | Main backgrounds, sidebar, header |
| #1A3A6B | Navy Mid | Cards, hover states, secondary bg |
| #B8960C | JP Heritage Gold | Accents, icons, active states |
| #1B6B35 | Positive Green | Income values, success states |
| #C0392B | Alert Red | Negative values, error states |
| #F0F4FA | Surface Light | Content card backgrounds, alt rows |
| #C8D6E8 | Border | Dividers, input borders, table lines |
| #1A2340 | Text Dark | Primary body text, headings |
| #4A5568 | Text Medium | Labels, secondary text |
| #FFFFFF | White | Form inputs, modal surfaces |

Token Definition File

/* globals.css or :root block */ :root { /* Brand */ --color-primary: #0D2545; /* Navy — main backgrounds */ --color-primary-mid: #1A3A6B; /* Navy mid — cards, hover */ --color-accent: #B8960C; /* JP Heritage Gold */ /* Surfaces */ --color-surface: #FFFFFF; --color-surface-alt: #F0F4FA; /* light blue-grey for card bg */ --color-border: #C8D6E8; /* Text */ --color-text-primary: #1A2340; --color-text-secondary: #4A5568; --color-text-muted: #7B8FA6; --color-text-inverse: #FFFFFF; /* Semantic */ --color-positive: #1B6B35; /* income, success */ --color-negative: #C0392B; /* expenses, errors */ --color-warning: #B8960C; /* pending, caution */ /* Interactive */ --color-btn-primary-bg: #0D2545; --color-btn-primary-fg: #FFFFFF; --color-btn-hover-bg: #1A3A6B; --color-link: #B8960C; }

Phase 3 — Brand Name Consolidation  (Days 2–3)

The portal currently displays two different brand names: the logo reads "JP Heritage" while footer legal text and metadata reference "Aurum Vault N.A." This inconsistency undermines trust — a critical failure in a financial product. All user-facing references must be unified under "JP Heritage."

Audit Checklist

| Task | File / Component | Priority | Est. Effort |
| --- | --- | --- | --- |
| Update page <title> tags | All HTML/page files | Critical | 30 min |
| Update Open Graph / meta description | index.html / _document.tsx | Critical | 20 min |
| Replace footer legal copy | Footer component | Critical | 30 min |
| Update 'About Aurum Vault' footer link | Footer component | High | 15 min |
| Replace all FDIC line references | Footer component | Critical | 20 min |
| Update logo alt text | Header / Navbar component | High | 10 min |
| Update browser tab favicon title | manifest / public/ | High | 15 min |
| Search codebase for 'Aurum Vault' | All source files (grep) | Critical | 45 min |

Find and Replace Strategy

Run a global search across the entire codebase for all variations before making manual edits. Do not rely on visual inspection alone — brand strings can appear in constants files, API responses, and configuration.

# Run in project root to find all occurrences grep -ri 'aurum vault' ./src --include='*.tsx' --include='*.ts' --include='*.css' --include='*.html' grep -ri 'aurum-vault' ./src grep -ri 'aurumvault' ./src # Expected replacements: # 'Aurum Vault' → 'JP Heritage' # 'Aurum Vault N.A.' → 'JP Heritage Bank N.A.' (or applicable legal name) # 'About Aurum Vault' → 'About JP Heritage'

Legal Copy Template

Member FDIC. Equal Housing Lender. © 2026 JP Heritage Bank N.A. All rights reserved.

ℹ  Confirm the correct legal entity name with your compliance or legal team before updating footer copy.

Phase 4 — Header Unification  (Days 3–4)

Currently the login page header uses a white/light background that visually disconnects from the green content area below. The dashboard uses a white topbar that sits above a green sidebar — creating two separate visual systems. The goal is to bring all header and navigation elements into the same deep navy system, so the page reads as a single cohesive product.

Login Page Header

The logo lockup at the top of the login screen should sit on the same navy or dark surface as the page — not float on an isolated white band. Two options:

- Option A (Recommended): Make the entire login page background navy (#0D2545) with the world map as a subtle dark overlay. The login card remains white/light surface for contrast.

- Option B: Apply navy to the header bar only, and keep the green background behind the card — this is a less complete fix but faster to implement.

/* Login page — full navy approach */ .login-page { background-color: var(--color-primary); background-image: url('/images/login-bg.jpg'); background-blend-mode: multiply; background-size: cover; } .login-header { background-color: transparent; /* inherits navy from parent */ border-bottom: 1px solid rgba(255,255,255,0.1); } .login-card { background-color: var(--color-surface); border: 1px solid var(--color-border); border-radius: 8px; box-shadow: 0 8px 32px rgba(0,0,0,0.24); }

Dashboard Topbar

The dashboard topbar (containing the JP Heritage logo, language selector, bell icon, and user avatar) should use the navy primary color to match the left sidebar, creating a continuous dark chrome around the light content area.

/* Dashboard topbar */ .topbar { background-color: var(--color-primary); border-bottom: 1px solid var(--color-primary-mid); color: var(--color-text-inverse); } .topbar .logo-text { color: #FFFFFF; } .topbar .icon-btn { color: rgba(255,255,255,0.8); } .topbar .icon-btn:hover { color: var(--color-accent); } /* Left sidebar */ .sidebar { background-color: var(--color-primary); border-right: 1px solid var(--color-primary-mid); } .sidebar .nav-icon { color: rgba(255,255,255,0.6); } .sidebar .nav-icon.active { color: var(--color-accent); }

Header Unification Scope

| Task | File / Component | Priority | Est. Effort |
| --- | --- | --- | --- |
| Login page header background | Login.css / LoginPage.tsx | High | 1 hr |
| Login page background blend mode | Login.css | High | 30 min |
| Dashboard topbar background | Topbar.css / Topbar.tsx | High | 1 hr |
| Sidebar top section color | Sidebar.css / Sidebar.tsx | High | 30 min |
| Topbar icon and text color updates | Topbar.css | Medium | 45 min |
| Logo variant (light on dark version) | Assets / brand files | High | 2 hrs |
| Active/hover state colors in sidebar | Sidebar.css | Medium | 45 min |

ℹ  If the JP Heritage logo is only available in a dark-on-light version, a white/reversed variant will need to be created for use on the navy header background.

Phases 5–6 — Login & Dashboard Restyle  (Days 4–7)

With tokens, brand, and header unified, the login page and dashboard are restyled component by component. The green backgrounds are replaced with navy surfaces, cards use the light blue-grey surface color, and all interactive elements adopt the new token values.

Key Visual Changes — Login Page

| Task | File / Component | Priority | Est. Effort |
| --- | --- | --- | --- |
| Page background color | LoginPage.css | High | 20 min |
| Login card shadow and border | LoginCard.css | Medium | 30 min |
| Input field borders and focus ring | Input.css | High | 45 min |
| Sign In button | Button.css | Critical | 20 min |
| Helper links (Forgot password etc.) | LoginPage.css | Medium | 20 min |
| Footer background | Footer.css | Medium | 20 min |

Key Visual Changes — Dashboard

| Task | File / Component | Priority | Est. Effort |
| --- | --- | --- | --- |
| Page/content background | Dashboard.css | High | 20 min |
| Quick Actions card backgrounds | QuickActions.css | High | 45 min |
| Stat card backgrounds | StatCard.css | High | 45 min |
| Total Balance / Income / Expense text | StatCard.css | Medium | 30 min |
| Overview chart area background | Chart.css | Medium | 1 hr |
| Recent Transactions panel | Transactions.css | Medium | 45 min |
| Upcoming & Pending section | PendingItems.css | Medium | 30 min |

Phases 7–8 — Inner Pages & QA  (Days 7–10)

Phase 7 — Inner Pages

Apply the same token-driven restyle to all inner pages: Money Transfer, Pay Bills, Add Transaction, View All Accounts, Settings, and Help. Because tokens are established in Phase 2, this largely involves removing green-specific overrides and letting the global styles apply.

| Task | File / Component | Priority | Est. Effort |
| --- | --- | --- | --- |
| Money Transfer page background | Transfer.css | High | 1 hr |
| Transfer form card surface | Transfer.css | High | 30 min |
| Transfer Limits panel | TransferSidebar.css | Medium | 30 min |
| Security Info panel | TransferSidebar.css | Medium | 20 min |
| Error/alert banner styling | Alert.css | High | 30 min |
| Progress bar (Transfer Limits used) | ProgressBar.css | Medium | 20 min |
| Remaining inner pages (repeat pattern) | Bills / Accounts / Settings | Medium | 3 hrs |

Phase 8 — QA & Accessibility Audit

Run a final audit across all pages and device sizes before shipping. Use an automated WCAG checker alongside manual inspection.

| Task | File / Component | Priority | Est. Effort |
| --- | --- | --- | --- |
| WCAG AA contrast check — all text | All pages | Critical | 2 hrs |
| WCAG contrast — buttons and icons | All pages | Critical | 1 hr |
| Cross-browser check (Chrome, Safari, FF) | All pages | High | 2 hrs |
| Mobile responsive check | All pages | High | 2 hrs |
| Search for remaining green values | All CSS files | High | 1 hr |
| Fix 'Failed to load accounts' error | Transfer page | High | 1 hr |
| Final stakeholder sign-off review | — | High | 2 hrs |

/* Quick grep to find any remaining hardcoded greens before shipping */ grep -rn '#[0-9a-fA-F]*[2-9][aA][0-9a-fA-F]' ./src/styles grep -rn 'green' ./src/styles grep -rn 'rgb(.*,.*[5-9][0-9],.*[0-5])' ./src/styles /* approx green check */

Delivery Summary

The four targeted changes represent a focused, high-impact rebrand that can be completed within a single sprint. The recommended sequence ensures that no phase blocks another and that the highest-risk issue (accessibility) is resolved on day one.

Total estimated effort: 8–10 working days · No new libraries required · All changes are pure CSS/asset-level except the brand text sweep

Success criteria: All WCAG AA contrast checks pass · Zero instances of 'Aurum Vault' in user-facing copy · Header chrome is visually continuous across login and dashboard · All primary buttons legible at arm's length

JP Heritage E-Portal  ·  Design Rebrand Implementation Plan  ·  v1.0  ·  February 2026